## Sheet1
Booking /Traveling Website (RedBus)
Serial No | Module Name | Task ID | Test Type | Test Scenario | Status | Remarks
1 | Homepage | TS.001 | Functional | Verify that the redBus logo redirects to the homepage when clicked. | Pass | Logo redirects correctly.
2 | Homepage | TS.002 | Functional | Ensure that the search bar accepts valid source and destination inputs and displays relevant bus options. | Pass | Search functionality works as expected.
3 | Homepage | TS.003 | UI | Check if the "Search Buses" button is clearly visible and clickable. | Pass | Button is prominent and responsive.
4 | Homepage | TS.004 | Functional | Test the "redDeal" feature to see if it applies discounts correctly during booking. | Pass | Discount applied successfully.
5 | Homepage | TS.005 | UI | Verify that the homepage loads within 3 seconds on a stable internet connection. | Pass | Load time approximately 2.8 seconds.
6 | Booking Page | TS.006 | Functional | Check if selecting a bus operator from the list updates the available seats and prices accordingly. | Pass | Seat and price updates are accurate.
7 | Train Listings Page | TS.007 | UI/UX | Verify if train class availability loads automatically without tapping | Fail | Seat info hidden behind "Tap to update"
8 | Booking Page | TS.008 | Functional | Test the "Track My Bus" feature to see if it provides real-time bus location updates. | Pass | Real-time tracking available.
9 | Booking Page | TS.009 | Functional | Verify that the "Cancel Booking" option is functional and prompts for confirmation. | Pass | Cancellation process works smoothly.
10 | Booking Page | TS.010 | UI | Check if the payment gateway is secure and supports multiple payment options. | Pass | Multiple payment methods supported.
11 | Booking Page | TS.011 | Functional | Test the "Reschedule" feature to see if it allows changing the travel date and time. | Pass | Rescheduling functionality works as expected.
12 | Booking Page | TS.012 | UI | Ensure that the booking summary displays correct details such as date, time, and operator. | Pass | Booking details are accurate.
13 | Booking Page | TS.013 | Functional | Verify that the "E-Ticket" is generated immediately after booking and accessible via email. | Pass | E-Ticket received promptly.
14 | Booking Page | TS.014 | Functional | Test the "redBus Unreserved" feature to see if it allows booking unreserved bus passes. | Pass | Unreserved booking functionality is operational.
15 | Booking Page | TS.015 | UI | Check if the website is responsive and displays correctly on mobile devices. | Pass | Mobile responsiveness is good.
16 | Booking Page | TS.016 | Functional | Test the "Safety+" feature to see if it provides information on safety measures and guidelines. | Pass | Safety+ information is provided.
17 | Home Page – Previously Viewed | TS.017 | Functional | Verify redirection works when clicking on a previously viewed journey card | Fail | Error page displayed instead of journey detail
18 | Login Page | TS.018 | Functional | Verify that the login page accepts valid credentials and redirects to the user dashboard. | Pass | Login process works as expected.
19 | Login Page | TS.019 | Functional | Check if the "Forgot Password" link functions and sends a reset link to the registered email. | Pass | Password reset functionality is operational.
20 | Login Page | TS.020 | UI | Ensure that the login page is user-friendly and error messages are clear. | Pass | UI is intuitive and messages are helpful.
21 | Support Page | TS.021 | Functional | Test the "Contact Us" form to see if it submits inquiries successfully. | Pass | Inquiry submission works smoothly.
22 | Support Page | TS.022 | Functional | Verify that the live chat support is responsive and provides timely assistance. | Pass | Live chat support is active.
23 | Support Page | TS.023 | Functional | Check if the FAQ section provides relevant and helpful information. | Pass | FAQ section is informative.
24 | Support Page | TS.024 | Functional | Test the "Call Us" feature to see if it connects to customer support without issues. | Pass | Call functionality is working.
25 | Support Page | TS.025 | UI | Ensure that the support page is easily accessible from the homepage and other pages. | Pass | Support page navigation is straightforward.
26 | Support Page | TS.026 | Functional | Verify that the support page loads within 3 seconds on a stable internet connection. | Pass | Load time approximately 2.5 seconds.